## Trang tính1
Tasks Name | Start Build | Finish Build | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes
Full page Airbnb(Home, Header, Footer, RoomDetail, Booking, pageNotFound, personal Info, login, register, roombyticket, Comment, Room Location) | 2023-10-10 | 2023-11-16 | 100% | Nguyễn Hoài Tiến | 2023-11-12 | 2023-11-16 | 100% | Nguyễn Hoài Tiến
Page Admin (AdminUser,AdminRoom,AdminLocaltion,AdminComment,AdminBookRoom, | 2023-10-10 | 2023-11-16 | 100% | Lê Kim Phước Tín | 2023-06-10 | 10/15/2023 | 100% | Lê Kim Phước Tín